## MAIN
No | Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration |  |  | Total | Iteration 1 | Iteration 2 | Iteration 3
1 | Login by username, password | User authorization | Simple | Iteration 1 | SE160296 | Vũ Thiên Ân | Iteration 1 | Nguyễn Phát Đạt | SE150694 | 15 | 6 | 4 | 5
2 | Login by gmail/facebook | User authorization | Medium | Iteration 1 | SE160199 | Nguyễn Đăng Lộc | Iteration 1 | Nguyễn Đăng Lộc | SE160199 | 14 | 4 | 5 | 5
3 | Reset password | User authorization | Medium | Iteration 1 | SE160221 | Nguyễn Vĩ Khang | Iteration 1 | Nguyễn Vĩ Khang | SE160221 | 14 | 6 | 5 | 3
4 | Register an account | Register | Simple | Iteration 1 | SE160199 | Nguyễn Phát Đạt | Iteration 1 | Vũ Thiên Ân | SE160296 | 15 | 5 | 5 | 5
5 | Register with gmail/facebook | Register | Medium | Iteration 1 | SE160199 | Nguyễn Đăng Lộc | Iteration 1
6 | Change user profile | Profile management | Simple | Iteration 1 | SE160199 | Nguyễn Phát Đạt | Iteration 1
7 | Change password | Profile management | Medium | Iteration 1 | SE160199 | Nguyễn Phát Đạt | Iteration 1
8 | View hostel list with paging | Hostel management | Medium | Iteration 1 | SE160296 | Vũ Thiên Ân | Iteration 1
9 | View hostel’s detail | Hostel management | Simple | Iteration 1 | SE160296 | Vũ Thiên Ân | Iteration 1
10 | View feedback of a hostel | Feedback management | Simple | Iteration 1 | SE160221 | Nguyễn Vĩ Khang | Iteration 1
11 | Toggle a favorite hostel | Favorite hostel | Simple | Iteration 1 | SE160221 | Nguyễn Vĩ Khang | Iteration 1
12 | View favorite hostel list | Favorite hostel | Simple | Iteration 1 | SE160221 | Nguyễn Vĩ Khang | Iteration 1
13 | View room list with paging | Room management | Medium | Iteration 1 | SE160199 | Nguyễn Đăng Lộc | Iteration 1
14 | View room’s detail | Room management | Simple | Iteration 1 | SE160199 | Nguyễn Đăng Lộc | Iteration 1
15 | Rent a room of a hostel | Room management | Simple | Iteration 1 | SE160199 | Nguyễn Phát Đạt | Iteration 1
16 | View landlord list with paging | Landlord management | Medium | Iteration 1 | SE160296 | Vũ Thiên Ân | Iteration 1
17 | View tenant list with paging | Tenant management | Simple | Iteration 1 | SE160296 | Vũ Thiên Ân | Iteration 2
18 | Cancel renting | Request processing | Simple | Iteration 1 | SE160221 | Nguyễn Vĩ Khang | Iteration 1
19 | Send announcement to tenants | Send/receive notifications | Simple | Iteration 1 | SE160199 | Nguyễn Phát Đạt | Iteration 1
20 | View landlord’s announcement | Send/receive notifications | Simple | Iteration 1 | SE160199 | Nguyễn Phát Đạt | Iteration 1
21 | Send request/recommendation/message to landlord | Send/receive notifications | Simple | Iteration 1 | SE160221 | Nguyễn Vĩ Khang | Iteration 1
22 | Add new feedback | Feedback management | Simple | Iteration 2 | SE160199 | Nguyễn Phát Đạt | Iteration 2
23 | Edit feedback | Feedback management | Simple | Iteration 2 | SE160199 | Nguyễn Phát Đạt | Iteration 2
24 | View room member list | Room management | Simple | Iteration 2 | SE160221 | Nguyễn Vĩ Khang | Iteration 2
25 | View service history | Service management | Simple | Iteration 2 | SE160199 | Nguyễn Đăng Lộc | Iteration 2
26 | View monthly invoice list | Payment management | Simple | Iteration 2 | SE160296 | Vũ Thiên Ân | Iteration 2
27 | View monthly invoice detail | Payment management | Simple | Iteration 2 | SE160296 | Vũ Thiên Ân | Iteration 2
28 | View contract list | Contract management | Simple | Iteration 2 | SE160199 | Nguyễn Phát Đạt | Iteration 2
29 | View contract detail | Contract management | Simple | Iteration 2 | SE160221 | Nguyễn Vĩ Khang | Iteration 2
30 | Add a tenant | Tenant management | Simple | Iteration 2 | SE160221 | Nguyễn Vĩ Khang | Iteration 2
31 | Remove a tenant | Tenant management | Simple | Iteration 2 | SE160199 | Nguyễn Đăng Lộc | Iteration 2
32 | View tenant’s detail | Tenant management | Simple | Iteration 2 | SE160199 | Nguyễn Đăng Lộc | Iteration 2
33 | Edit tenant’s information | Tenant management | Simple | Iteration 2 | SE160199 | Nguyễn Đăng Lộc | Iteration 2
34 | Activate/Deactivate a tenant account | Tenant management | Simple | Iteration 2 | SE160199 | Nguyễn Phát Đạt | Iteration 2
35 | Edit hostel’s detail | Hostel management | Simple | Iteration 2 | SE160296 | Vũ Thiên Ân | Iteration 2
36 | Activate/Deactivate a hostel | Hostel management | Simple | Iteration 2 | SE160296 | Vũ Thiên Ân | Iteration 2
37 | View general report of a specific hostel | Hostel management | Simple | Iteration 2 | SE160199 | Nguyễn Đăng Lộc | Iteration 2
38 | Filter hostel by search, by droplist | Hostel management | Simple | Iteration 2 | SE160296 | Vũ Thiên Ân | Iteration 2
39 | View landlord’s detail | Landlord management | Simple | Iteration 2 | SE160221 | Nguyễn Vĩ Khang | Iteration 2
40 | Activate/Deactivate a landlord account | Landlord management | Simple | Iteration 2 | SE160221 | Nguyễn Vĩ Khang | Iteration 2
41 | Add a room | Room management | Simple | Iteration 3 | SE160296 | Vũ Thiên Ân | Iteration 3
42 | Remove a room | Room management | Simple | Iteration 3 | SE160296 | Vũ Thiên Ân | Iteration 3
43 | Edit room’s detail | Room management | Simple | Iteration 3 | SE160296 | Vũ Thiên Ân | Iteration 3
44 | View room member list | Room management | Simple | Iteration 3 | SE160221 | Nguyễn Vĩ Khang | Iteration 3
45 | Add a room member | Room management | Simple | Iteration 3 | SE160221 | Nguyễn Vĩ Khang | Iteration 3
46 | Edit room member information | Room management | Simple | Iteration 3 | SE160221 | Nguyễn Vĩ Khang | Iteration 3
47 | Edit invoice detail | Payment management | Simple | Iteration 3 | SE160296 | Vũ Thiên Ân | Iteration 3
48 | Add a payment invoice | Payment management | Simple | Iteration 3 | SE160296 | Vũ Thiên Ân | Iteration 3
49 | Send request to add a hostel | Send/receive notifications | Simple | Iteration 3 | SE160199 | Nguyễn Phát Đạt | Iteration 3
50 | View revenue statistics of a specific hostel | Statistic | Simple | Iteration 3 | SE160199 | Nguyễn Đăng Lộc | Iteration 3
51 | View revenue statistics of a specific room | Statistic | Simple | Iteration 3 | SE160199 | Nguyễn Đăng Lộc | Iteration 3
52 | Export report to excel file | Export data | Simple | Iteration 3 | SE160199 | Nguyễn Đăng Lộc | Iteration 3
53 | Approve a landlord’s request | Request processing | Simple | Iteration 3 | SE160199 | Nguyễn Đăng Lộc | Iteration 3
54 | Approve a rental request | Request processing | Simple | Iteration 3 | SE160199 | Nguyễn Đăng Lộc | Iteration 3
55 | View service list | Service management | Simple | Iteration 3 | SE160199 | Nguyễn Phát Đạt | Iteration 3
56 | Edit service details | Service management | Simple | Iteration 3 | SE160199 | Nguyễn Phát Đạt | Iteration 3
57 | Add a service | Service management | Simple | Iteration 3 | SE160199 | Nguyễn Phát Đạt | Iteration 3
58 | Remove a service | Service management | Simple | Iteration 3 | SE160199 | Nguyễn Phát Đạt | Iteration 3