## W01
PROJECT REPORT
Group | Dolphin
Week | 09/05/2022 - 15/05/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Choose topic | Completed | The whole team agreed to choose the topic hostel management.
2 | Set up meeting schedule | Completed | Google meet on Tuesday and Thursday for 1 hour / session
3 | Choose technology and tools | In Progress | Java(Spring boot), HTML/CSS/JS, Git, Jira
4 | Start Project on Jira | Completed | Started project and added members
5 | Get requirements | Completed | Selected the appropriate requirements from the ideas of the members.
5 | Write sketch document | Completed | Wrote SRS document(Introduction, System Functions)
6 | Discuss on google meet on Tuesday | Completed | All members disscuss, update document.
7 | Discuss on google meet on Thursday | Completed | All members disscuss, update document.
# | Project Task | Member | Notes (Task Details, etc.)
1 | Choose topic and system functions | All | The whole team contributed ideas to get the final result.
2 | Context diagram | All | Produced together on diagrams.io
3 | Screen flow | Lộc, Khang | The whole team reviewed and modified Loc and Khang's draft.
4 | Screen details | All | It was developed from the screen flow.
5 | Backlog | Ân | Current version is only the first draft and not detailed
6 | Weekly report | Ân, Đạt | Wrote weekly report of first week
7 | Discuss on google meet | All | 20h-23h.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Subclasses in Context Diagram | Completed | #NA
2 | Use QR code to rent hostel | Completed | It is not suitable for the team.
3 | Allow one account to have 2 roles | Completed | Each account has only one role and it is determined after registration.
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Add document content. | 21/5/2022 | #NA
2 | Find the suitable template. | 19/5/2022 | #NA
3 | Design database. | 21/5/2022 | #NA
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | Modify the topic(change to short-term) | Vũ Thiên Ân | Change to short-term room rental to make it more interesting
2 | I suggest not using the framework | Đạt | It takes a long time to learn framework so perhaps we will not manage to use framework

## W02
PROJECT REPORT
Group | Dolphin
Week | 16/05/2022 - 22/05/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Refining ERD | In Progress | Contraints on fields are still not finalized
2 | Sketching wireframes for a number of screens | In Progress | Layouts of many screens were designed using figma
3 | Screen details | Completed | Discuss on google meet and in class.
4 | User authorization | Completed | Choose roles for each screen
5 | Backlog | In Progress | Based on SRS document
6 | Implementing entities demo | Completed | Creation and addition services of 2 entities, hostel and landlord, using Spring boot, Hibernate and Thymeleaf, were mostly done.
7 | Discuss on google meet on Tuesday | Completed | All members disscuss, update SRS document, ERD.
8 | Discuss on google meet on Thursday | Completed | All members disscuss, update SRS document, ERD.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Design entities and draft ERD | Ân, Đạt | Mostly done by Ân and Đạt, reviewed by team.
2 | Sketching wireframes for a number of screens | Lộc | Mostly done by Lộc, reviewed by team.
3 | Screen details (SRS) | Lộc, Khang | Mostly done by Lộc and Khang, reviewed by team
4 | User authorization (SRS) | Lộc, Khang | Done by Lộc and Khang
5 | Backlog | Ân, Đạt | Ân write function name, Đạt update feature
6 | Weekly report | Ân, Đạt | Wrote weekly report of second week
7 | Implementing entities demo | Ân | Self-study and implement it.
8 | Discuss on google meet | All | 20h-23h.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Design database to support filtering by address | Completed | #NA
2 | Populating database | In Progress | #NA
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Finalizing database | 29/5/2022 | #NA
2 | Complete SRS document | 29/5/2022 | #NA
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | #NA | #NA | #NA

## W03
PROJECT REPORT
Group | Dolphin
Week | 23/05/2022 - 29/05/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Finalizing ERD | Completed | #NA
2 | Updating SRS document | Completed | #NA
3 | Creating database for user entities, tenants and landlords | Completed | #NA
4 | Designing templates for pages with user functions on Figma | Completed | #NA
5 | Implementing DAO and Controller classes for user entities, tenants and landlords | Completed | #NA
6 | Creating repository on GitHub | Completed | #NA
6 | Discuss on google meet on Tuesday | Completed | All members disscuss, update document, ERD, backlog.
7 | Discuss on google meet on Thursday | Completed | All members disscuss, update document, ERD, backlog.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Finalizing ERD | All | #NA
2 | Updating SRS document | Khang, Lộc | #NA
3 | Creating database for user entities, tenants and landlords | Ân | #NA
4 | Designing templates for pages with user functions on Figma | Lộc | #NA
5 | Implementing DAO and Controller classes for user entities, tenants and landlords | Ân | #NA
6 | Creating repository on GitHub | Đạt | #NA
7 | Discuss on google meet | All | 20h-23h.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | #NA |  | #NA
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Start coding | 2022-05-06 | #NA
2 | Create databse | 2022-05-07 | #NA
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | #NA | #NA | #NA

## W04
PROJECT REPORT
Group | Dolphin
Week | 30/05/2022 - 05/06/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Complete DTO package | Completed
2 | Finalizing ERD | Completed
3 | Finalizing database | Completed
4 | Discuss on google meet on Tuesday | Completed | All members disscuss, update document, ERD, DTO.
5 | Discuss on google meet on Thursday | Completed | All members disscuss, update document, ERD, DTO.
6 | Find template | In Progress | Find the suitable template
7 | Code Header + hostel-list.jsp view | Completed
8 | Code Footer + homepage.jsp view | Completed
9 | Code functions BE | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Complete DTO package | Đạt
2 | Finalizing ERD | All team
3 | Finalizing database | Ân
4 | Discuss on google meet | All
5 | Find template | Đạt, Lộc
6 | Code Header + hostel-list.jsp view | Đạt
7 | Code Footer + homepage.jsp view | Lộc
8 | Code hostel list, display option, login | Ân
9 | Code reset password, change password, register | Khang
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | The program does not receive the path(a href, servlet) | In Progress | All
2 | Conflict code when pulling code from github. | Completed | Đạt
3 | Can't push code to remote repository | In Progress | Khang
4 | Netbeans doesn't work. | Pending | Lộc can't code because can't start netbeans
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Complete functions with hostel management, room management.
2 | Complete templates relevant hostel management, room management.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W05
PROJECT REPORT
Group | Dolphin
Week | 06/06/2022 - 12/06/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Discuss on google meet on Tuesday | Completed | All members disscuss, assign tasks for members.
2 | Redefine path of project | Completed
3 | Recode change password, login, reset password | Completed
4 | Fix css of page: 'Login', 'Register', 'Homepage' | In Progress
5 | Code 'user-profile' page | Completed
6 | Discuss on google meet on Thursday | Completed
7 | Code FE and BE for Hostel Detail | Completed
8 | Code ajax for toggle favorite and favorite button | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Redefine path of project | Đạt
2 | Recode change password, login, reset password | Khang
3 | Fix css of page: 'Login', 'Register', 'Homepage' | Lộc
4 | Discuss on google meet | All
5 | Code 'user-profile' page FE | Lộc
6 | Code 'user-profile' page BE | Khang
7 | Code FE and BE for Hostel Detail | Đạt
8 | Code ajax for toggle favorite and favorite button | Ân
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
NA | NA
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Finalizing hostel list and detail (UX, UI) | 19/06/2022
2 | Code room type and room detail | 19/06/2022
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
NA | NA

## W06
PROJECT REPORT
Group | Dolphin
Week | 13/06/2022 - 19/06/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Discuss on google meet on Tuesday | Completed | All members disscuss, assign tasks for members.
2 | Code search address with ajax | Completed
3 | Keep search address | Completed
4 | Code search address on homepage | In Progress
5 | Draw wiframe | Completed
6 | Discuss on google meet on Thursday | Completed
7 | Redefine database | Completed
8 | Code ContractDAO, roomDAO, InvoiceDAO | Completed
9 | Write document | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Discuss on google meet | All
2 | Code search address with ajax | Đạt
3 | Keep search address | Đạt
4 | Code search address on homepage | Ân
5 | Draw wiframe | Lộc
6 | Redefine database | Đạt, Khang
7 | RoomDAO | Khang
8 | Code ContractDAO, InvoiceDAO | Ân
9 | Support draw wiframe | Ân
10 | Write document | All
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
NA | NA
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Code FE for room, invoice, contract and combine with BE | 26/06/2022
2 | Complete all document | 26/06/2022
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
NA | NA

## W07
PROJECT REPORT
Group | Dolphin
Week | 20/06/2022 - 26/06/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Discuss on google meet on Tuesday | Completed | All members disscuss, assign tasks for members.
2 | Discuss on google meet on Thursday | Completed | All members disscuss, assign tasks for members.
3 | Write design document | Completed | All member
4 | Code booking request | In Progress | Khang
5 | Code service | In Progress | Lộc
6 | Code invoice | In Progress | Ân
7 | Code contract | In Progress | Đạt
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Discuss on google meet | All
2 | Write design document | All
3 | Code booking request | Khang
4 | Code service | Lộc
5 | Code invoice | Ân
6 | Code contract | Đạt
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
NA | NA
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Complete 2 main flow | 2022-03-07
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
NA | NA | NA | NA

## W08
PROJECT REPORT
Group | Dolphin
Week | 27/06/2022 - 02/07/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Discuss on google meet on Tuesday | Completed | All members disscuss, assign tasks for members.
2 | Discuss on google meet on Thursday | Completed | All members disscuss, assign tasks for members.
3 | Code invoice function | Completed
4 | Code hostel function | In Progress
5 | Code service function | In Progress
6 | Code room type function | In Progress
7 | Code room function | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Discuss on google meet | All
2 | Update design document | All
3 | Code admin function | Khang
4 | Code room, roomtype, service, room resident, hostel function (landlord) | Đạt
5 | Code invoice function (landlord), check valid form. | Ân
6 | Code UI, add, delete images for hostel and roomtype (landlord) | Lộc
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
NA | NA
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Complete all main flow | 2022-10-07
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
NA | NA | NA | NA

## W09
PROJECT REPORT
Group | Dolphin
Week | 11/07/2022 - 17/07/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Discuss on google meet on Tuesday | Completed | All members disscuss, assign tasks for members.
2 | Discuss on google meet on Thursday | Completed | All members disscuss, assign tasks for members.
3 | Code resident function | In Progress
4 | Code revenue function | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Discuss on google meet | All
2 | Update design document | All
3 | Code UI for resident function | Đạt
4 | Code CRUD functions for resident | Đạt
5 | Code back-end for revenue functions | Khang
6 | Code UI for revenue list, revenue detail | Lộc
7 | Fix bug: register functions | Ân
8 | Update add invoice, view invoice detail | Ân
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
NA | NA
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Complete all main flow | 2022-10-07
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
NA | NA | NA | NA